## Slide 1
year 1
year 2
year 3
Reduction of NGC filament Hα (Siena)
Fall 2019 team foreign meeting
Anticipated project start (Jan 2018) Graduate Student (KU)
Fall 2020 team meeting
Fall 2018 team meeting
Finish H-alpha observations for NGC 5353 Filament
Completion of H-alpha reduction pipeline (Siena)
Disseminate preliminary results at domestic conference
Disseminate final results at international conference
Paper: Spatial dist of Hα/dust in NGC filament
Implementation of SAMs Millenium, cluster zoom, and constrained local simulation (Trieste)
Paper: Constrain stripping and starvation in models with gas/dust profiles
Size measurements from WISE 12um data (Siena)
H-alpha observing campaign for Leo Filaments
Paper: Effect of environment on total UV+22um SFR, CO, HI, and dust
CO and HI observing & reduction (EPFL/Paris)
Paper: Spatial distribution of H-alpha/dust in Leo filaments (data release)
Paper: Constrain stripping and starvation in models with total gas
Hα & WISE
CO/HI
Theory
Meetings
Reduction and analysis of Leo filament Halpha data (KU)
Analysis of NGC filament Hα (KU)
H2 and HI mass derivation (KU)
Compare SAM results to integrated data (Trieste/KU/Siena)
Blue denotes work funded by this proposal.
Disseminate results at domestic conference
Completion of data acquisition phase
Red denotes publication.
Compare SAM results to resolved data (Trieste/KU/Siena)